## RTM
Requirement ID | Requirement Description | Test Scenario ID(s) | Test Case ID(s) | Test Execution Status | Defect ID (if any) | Coverage Status
REQ-AUTH-01 | User shall be able to register with valid details | SCN-001 | TC-AUTH-001 | Pass |  | Covered
REQ-PROP-01 | Agent shall be able to create a property listing | SCN-PM-001 | TC-PM-001 | Pass |  | Covered
REQ-SRCH-01 | User shall be able to search properties by city | SCN-SF-001 | TC-SF-001 | Pass |  | Covered
REQ-AI-01 | System shall recommend properties for new users | SCN-AI-001 | TC-AI-001 | Pass |  | Covered
REQ-FAV-01 | User shall be able to add property to favorites | SCN-FAV-001 | TC-FAV-001 | Fail | BUG-101 | Covered
REQ-ADM-01 | Admin shall be able to view all users | SCN-ADM-001 | TC-ADM-001 | Pass |  | Covered
REQ-SEC-01 | Unauthorized users shall not access admin panel | SCN-SEC-001, SCN-ADM-006 | TC-SEC-001, TC-ADM-004 | Pass |  | Covered
REQ-API-01 | API shall return paginated property data | SCN-API-001 | TC-API-001 | Pass |  | Covered